## Sheet 1
Color Coding |  |  | Completed |  |  |  | FALL 2022 SEMESTER
|  |  | In Progress | [6 empty] | Yom Kippur |  |  |  |  | midterm |  |  |  |  | final
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2022-09-13 | 2022-09-18 | 100%
| Confirm Project Team Roles |  | ALL | 2022-09-13 | 2022-09-25 | 100%
| Develop two business cases |  | ALL | 2022-09-13 | 2022-09-18 | 100%
| Develop Project Initiation Document (PID) |  | ALL | 2022-09-20 | 2022-09-25 | 100%
| Produce initial Project Plan, RACI |  | Kishore Kanchan, Rufan Miganiyev | 2022-10-04 | 2022-10-09 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Melika Zandikarimi | 2022-10-11 | 2022-10-15 | 100%
| Produce Context Diagram, Define System Interfaces |  | Jianan Jiang | 2022-10-11 | 2022-10-15 | 100%
| Define Business Requirements |  | Melika Zandikarimi | 2022-10-11 | 2022-10-23 | 100%
| Agree to System Requirements types |  | ALL | 2022-10-18 | 2022-10-23 | 100%
| Define Functional Decomposition |  | Jianan Jiang | 2022-10-18 | 2022-10-23 | 100%
| Produce RCT document |  | Jianan Jiang | 2022-10-18 | 2022-10-23 | 100%
| Decide which features to implement this semester |  | ALL | 2022-10-25 | 2022-10-30 | 100%
| Produce analysis diagrams (UML, DFD) |  | Jianan Jiang | 2022-10-25 | 2022-10-30 | 100%
| Define functional requirements (User Stories) |  | Jianan Jiang | 2022-10-25 | 2022-10-30 | 100%
| Update Project Plan with additional requirements tasks |  | Zo DiSanto | 2022-10-11 | 2022-12-04 | 80%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Shanshan Li | 2022-11-15 | 2022-11-20 | 100%
| Database Design (ERD, Table spec) |  | Rufan Mirganiyev | 2022-11-08 | 2022-11-13 | 100%
| System Interface Design |  | Shanshan Li | 2022-11-22 | 2022-11-27 | 100%
| User Interface design |  | Kishore Kanchan | 2022-11-22 | 2022-11-27 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Establish code repository in GitHub |  | Shanshan Li | 2022-10-30 | 2022-11-08 | 100%
| Create an Account | GUI & Functionality Detailed Design | Kishore Kanchan | 2022-10-25 | 2022-11-08 | 75%
|  | Coding | Shanshan Li | 2022-11-01 | 2022-11-08 | 75%
| Sign into an Account | GUI & Functionality Detailed Design | Kishore Kanchan | 2022-10-25 | 2022-11-15 | 75%
|  | Coding | Shanshan Li | 2022-10-25 | 2022-11-15 | 75%
| Delete an Account | GUI & Functionality Detailed Design | Kishore Kanchan | 2022-11-15 | 2022-11-22 | 0%
|  | Coding | Shanshan Li | 2022-11-15 | 2022-11-22 | 0%
| Modify General Users' Information | GUI & Functionality Detailed Design | Kishore Kanchan | 2022-11-22 | 2022-11-29 | 0%
|  | Coding | Shanshan Li | 2022-11-22 | 2022-11-29 | 0%
| Update Password | GUI & Functionality Detailed Design | Kishore Kanchan | 2022-11-29 | 2022-12-06 | 0%
|  | Coding | Shanshan Li | 2022-11-29 | 2022-12-06 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document for user profile (Buyer Account) |  | Louise Ngo | 2022-11-29 | 2022-12-06 | 50%
| Evaluate Buyer Sign in Components to be Tested |  | Jianan Jiang | 2022-11-29 | 2022-12-06 | 50%
| Create an Account | Design Test Cases | Louise Ngo | 2022-12-02 | 2022-12-04 | 50%
|  | Execute Test Cases | Louise Ngo | 2022-12-02 | 2022-12-04 | 50%
|  | Anaylze Test Results | ALL | 2022-12-02 | 2022-12-04 | 50%
| Sign into an Account | Design Test Cases | Louise Ngo | 2022-12-04 | 2022-12-06 | 50%
|  | Execute Test Cases | Louise Ngo | 2022-12-04 | 2022-12-06 | 50%
|  | Anaylze Test Results | ALL | 2022-12-04 | 2022-12-06 | 50%
| Delete an Acount | Design Test Cases | Louise Ngo | 2022-12-06 | 2022-12-08 | 0%
|  | Execute Test Cases | Louise Ngo | 2022-12-06 | 2022-12-08 | 0%
|  | Anaylze Test Results | ALL | 2022-12-06 | 2022-12-08 | 0%
| Modify General User's Information | Design Test Cases | Louise Ngo | 2022-12-08 | 2022-12-11 | 0%
|  | Execute Test Cases | Louise Ngo | 2022-12-08 | 2022-12-11 | 0%
|  | Anaylze Test Results | ALL | 2022-12-08 | 2022-12-11 | 0%
| Update Password | Design Test Cases | Louise Ngo | 2022-12-11 | 2022-12-13 | 0%
|  | Execute Test Cases | Louise Ngo | 2022-12-11 | 2022-12-13 | 0%
|  | Anaylze Test Results | ALL | 2022-12-11 | 2022-12-13 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation |  | Prepare Application Demo for the Presentation | ALL | 2022-12-13 | 2022-12-20 | 0%