## Road Map
Features implemented last semester |  |  | Revolution Art Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | I1 - 03/10/2023 | I2 - 03/31/2023 | I3 - 04/21/2023 | I4 - 05/12/2023
Module 1 - Buyer Account (Subscribed Clients) | 01.01 Create an Account
01.02 Sign into Account
| 01.03 Delete an Account | 4 | x
| 01.04 Modify General User's Information | 4 |  | x
| 01.05 Review and Choose Subscription Plan | 3 |  | x
| 01.06 Update Password | 4 |  | x
| 01.11 See History of Purchase | 4 |  |  |  | x
| 01.12 Rate Artwork, Artist, Services | 4 |  |  | x
Module 2 - Seller Account (Galleries) | 02.01 Create an Account | 3 | x
| 02.02 Sign into Account | 3 | x
| 02.03 Delete an Account | 4 | x
| 02.04 Modify General User's Information | 4 |  | x
| 02.05 Add Artworks | 4 |  |  | x
| 02.06 Remove Artworks | 4 |  |  | x
| 02.07 Modify Artwork Information | 4 |  |  | x
| 02.08 Update Password | 3 |  | x
| 02.11 Review and Choose Subscription Plan | 3 |  | x
Module 4 - Shopping Cart | 04.01 Make Payment | 4 |  |  |  | x
| 04.02 Modify Shopping Cart | 3 |  |  |  | x
| 04.03 Add Items to Shopping Cart | 3 |  |  |  | x
| 04.04 Remove Items from Shopping Cart | 3 |  |  |  | x
|  | VELOCITY: | 14 | 21 | 16 | 17

## StoryMap
Epics |  | Revolution Art - User Story Map
Epic 1 - Buyer Account |  | Epic 1 - Buyer Account | Epic 2 - Seller Account | Epic 3 - Shopping Cart
Epic 2 - Seller Account | User Stories | 01.03 Delete an Account | 02.01 Create an Account
Epic 3 - Shopping Cart |  |  | 02.02 Sign into Account
|  |  | 02.03 Delete an Account |  | Iteration 1
|  | 01.04 Modify General User's Information | 02.04 Modify General User's Information
|  | 01.05 Review and Choose Subscription Plan | 02.08 Update Password
|  | 01.06 Update Password | 02.11 Review and Choose Subscription Plan |  | Iteration 2
|  | 01.12 Rate Artwork, Artist, Services | 02.05 Add Artworks
02.06 Remove Artworks
|  |  | 02.07 Modify Artwork Information |  | Iteration 3
|  | 01.11 See History of Purchase |  | 04.01 Make Payment
04.02 Modify Shopping Cart
04.03 Add Items to Shopping Cart
|  |  |  | 04.04 Remove Items from Shopping Cart | Iteration 4

## Kanban Board
Sorted by Epic