## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 01. Buyer Account | 1.03 | Delete an Account | Implement core functionality & DF-Out & DF-In | 2023-03-01 | 2023-03-02 | 100% | Shanshan Li | LEGEND
2 | 01. Buyer Account | 1.03 | Delete an Account | Implement CN | 2023-03-01 | 2023-03-02 | 100% | Shanshan Li
3 | 01. Buyer Account | 1.03 | Delete an Account | Implement GUI requirements | 2023-03-01 | 2023-03-02 | 100% | Shanshan Li
4 | 01. Buyer Account | 1.03 | Delete an Account | Develop Test Cases for Delete Account functionality | 2023-03-02 | 2023-03-03 | 100% | Louise Ngo
5 | 01. Buyer Account | 1.03 | Delete an Account | Test Delete Account functionality | 2023-03-02 | 2023-03-03 | 100% | Louise Ngo
11 | 02. Seller Account | 2.01 | Create an Account | Implement core functionality & DF-Out, ET-Ex | 2023-02-23 | 2023-02-24 | 100% | Shanshan Li
12 | 02. Seller Account | 2.01 | Create an Account | Implement FV & CN | 2023-02-23 | 2023-02-24 | 100% | Shanshan Li
13 | 02. Seller Account | 2.01 | Create an Account | Implement GUI requirements | 2023-02-23 | 2023-02-24 | 100% | Shanshan Li
14 | 02. Seller Account | 2.01 | Create an Account | Develop Test Cases for Create Account functionality | 2023-02-24 | 2023-02-25 | 100% | Louise Ngo
15 | 02. Seller Account | 2.01 | Create an Account | Test Create Account functionality | 2023-02-24 | 2023-02-25 | 100% | Louise Ngo
16 | 02. Seller Account | 2.02 | Sign Into Account | Implement core functionality & DF-In, DF-Out, ET-Ex | 2023-02-26 | 2023-02-27 | 100% | Shanshan Li
17 | 02. Seller Account | 2.02 | Sign Into Account | Implement FV & CN | 2023-02-26 | 2023-02-27 | 100% | Shanshan Li
18 | 02. Seller Account | 2.02 | Sign Into Account | Implement GUI requirements | 2023-02-26 | 2023-02-27 | 100% | Shanshan Li
19 | 02. Seller Account | 2.02 | Sign Into Account | Develop Test Cases for Sign Into Account functionality | 2023-02-27 | 2023-02-28 | 100% | Louise Ngo
20 | 02. Seller Account | 2.02 | Sign Into Account | Test Sign Into Account functionality | 2023-02-27 | 2023-02-28 | 100% | Louise Ngo
21 | 02. Seller Account | 2.03 | Delete an Account | Implement core functionality & DF-Out & DF-In | 2023-03-03 | 2023-03-04 | 100% | Shanshan Li
22 | 02. Seller Account | 2.03 | Delete an Account | Implement CN | 2023-03-03 | 2023-03-04 | 100% | Shanshan Li
23 | 02. Seller Account | 2.03 | Delete an Account | Implement GUI requirements | 2023-03-03 | 2023-03-04 | 100% | Shanshan Li
24 | 02. Seller Account | 2.03 | Delete an Account | Develop Test Cases for Delete Account functionality | 2023-03-04 | 2023-03-05 | 100% | Louise Ngo
25 | 02. Seller Account | 2.03 | Delete an Account | Test Delete Account functionality | 2023-03-04 | 2023-03-05 | 100% | Louise Ngo

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 03. Admin Home | 3.01 | View Subscriptions | Search for a proper API | 2018-10-22 | 2018-10-23 | 100% | Sakar Dekate
2 | 03. Admin Home | 3.01 | View Subscriptions | Implement API | 2018-10-22 | 2018-10-23 | 100% | Sakar Dekate
3 | 03. Admin Home | 3.01 | View Subscriptions | Display all subscription | 2018-10-24 | 2018-10-25 | 100% | Sakar Dekate
4 | 03. Admin Home | 3.01 | View Subscriptions | Implement core functionality | 2018-10-24 | 2018-10-25 | 100% | Sakar Dekate
5 | 03. Admin Home | 3.01 | View Subscriptions | Implement GUI requirments | 2018-10-24 | 2018-10-25 | 100% | Sakar Dekate
6 | 03. Admin Home | 3.01 | View Subscriptions | Test View Courses functionality | 2018-10-26 | 2018-10-26 | 100% | Sakar Dekate
6 | 06. Faculty Home | 6.02 | Add/Delete Student | Search for a proper API | 2018-10-26 | 2018-10-26 | 100% | Sakar Dekate
7 | 06. Faculty Home | 6.02 | Add/Delete Student | Implement API | 2018-10-26 | 2018-10-27 | 100% | Avinash Mudduluru
8 | 06. Faculty Home | 6.02 | Add/Delete Student | Create Add Button | 2018-10-27 | 2018-10-27 | 100% | Avinash Mudduluru
9 | 06. Faculty Home | 6.02 | Add/Delete Student | Create Delete Button | 2018-10-27 | 2018-10-28 | 100% | Avinash Mudduluru
10 | 06. Faculty Home | 6.02 | Add/Delete Student | Show the updated students list | 2018-10-28 | 2018-10-28 | 100% | Avinash Mudduluru
11 | 06. Faculty Home | 6.02 | Add/Delete Student | Implement core functionality | 2018-10-28 | 2018-10-28 | 100% | Avinash Mudduluru
12 | 06. Faculty Home | 6.02 | Add/Delete Student | Implement GUI requirments | 2018-10-28 | 2018-10-29 | 100% | Avinash Mudduluru
13 | 06. Faculty Home | 6.02 | Add/Delete Student | Test Add/Delete Course | 2018-10-29 | 2018-10-30 | 100% | Avinash Mudduluru
11 | 08. Technical Support | 8.01 | Report a Bug | Display Report a bug button | 2018-10-31 | 2018-10-31 | 100% | Akshay More
12 | 08. Technical Support | 8.01 | Report a Bug | Create a report bug form | 2018-10-31 | 2018-10-31 | 100% | Akshay More
13 | 08. Technical Support | 8.01 | Report a Bug | Implement core functionality | 2018-11-01 | 2018-11-01 | 100% | Akshay More
14 | 08. Technical Support | 8.01 | Report a Bug | Implement GUI requirments | 2018-11-01 | 2018-11-01 | 100% | Akshay More
15 | 08. Technical Support | 8.01 | Report a Bug | Test Report a Bug | 2018-11-01 | 2018-11-02 | 100% | Akshay More
16 | 08. Technical Support | 8.02 | Ask for assistance | Display Technical Support contact details | 2018-11-02 | 2018-11-02 | 100% | Aishwarya Aroll