## Road Map
Features implemented last semester (Fall 2022)
Features implemented this semester (Spring 2023) |  |  | Revolution Art Application
Features implemented in future scope |  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | I1 - 03/10/2023 | I2 - 03/31/2023 | I3 - 04/21/2023 | I4 - 05/12/2023
Module 1 - Buyer Account (Subscribed Clients) | 01.01 Create an Account
01.02 Sign into Account
| 01.03 Delete an Account | 4 | x
| 01.04 Modify General User's Information | 4 |  | x
| 01.05 Review and Choose Subscription Plan | 3 |  | x
| 01.06 Update Password | 4 |  | x
| 01.08 Cancel Subscription Plan | 6 |  |  |  | x
01.09 Agree to Privacy Conditions
01.10 Contact Customer Support
01.11 See History of Purchase
| 01.12 Like Artwork, Artist, Services. | 5 |  |  |  | x
Module 2 - Seller Account (Galleries) | 02.01 Create an Account | 3 | x
| 02.02 Sign into Account | 3 | x
| 02.03 Delete an Account | 4 | x
| 02.04 Modify General User's Information | 4 |  | x
| 02.05 Add Artworks | 5 |  |  | x
| 02.06 Remove Artworks | 5 |  |  | x
| 02.07 Modify Artwork Information | 6 |  |  | x
| 02.08 Update Password | 3 |  | x
02.09 Agree to Privacy Conditions
02.10 Contact Customer Support
| 02.11 Review and Choose Subscription Plan | 3 |  | x
| 02.12 Cancel Subscription | 6 |  |  |  | x
Module 3 - Searching | 03.01 Select Artwork by Created Time
03.02 Select Artwork by Art Types
03.03 Select Artwork by Artwork Authors
03.04 Select Artwork by Artwork Sellers
Module 4 - Shopping Cart | 04.01 Make Payment
04.02 Modify Shopping Cart
04.03 Add Items to Shopping Cart
04.04 Remove items from shopping cart
Module 5 - Subscription Plan | 05.01 Make Payment
05.02 Receive Sales Program Weekly
05.03 Receive Artwork Report
05.04 Receive Discount
|  | VELOCITY: | 14 | 21 | 16 | 17

## StoryMap
Epics |  | Revolution Art - User Story Map
Epic 1 - Buyer Account |  | Epic 1 - Buyer Account | Epic 2 - Seller Account
Epic 2 - Seller Account | User Stories | 01.03 Delete an Account | 02.01 Create an Account
02.02 Sign into Account
|  |  | 02.03 Delete an Account | Iteration 1
|  | 01.04 Modify General User's Information | 02.04 Modify General User's Information
|  | 01.05 Review and Choose Subscription Plan | 02.08 Update Password
|  | 01.06 Update Password | 02.11 Review and Choose Subscription Plan | Iteration 2
02.05 Add Artworks
02.06 Remove Artworks
|  |  | 02.07 Modify Artwork Information | Iteration 3
|  | 01.08 Cancel Subscription Plan | 02.12 Cancel Subscription
|  | 01.12 Like Artwork, Artist, Services. |  | Iteration 4