## Sheet 1
Color Coding |  | Completed |  |  |  | FALL 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2022-09-21 | 2022-10-02 | 2022-10-18 | 2022-10-25 | 2022-10-30 | 2022-11-02 | 2022-11-07 | 2022-11-15 | 2022-11-29 | 2022-11-22 | 2022-11-29 | 2022-12-02 | 2022-12-07 | 2022-12-13 | 2022-12-15
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2022-09-13 | 2022-09-19 | 100%
| Confirm Project Team Roles | ALL | 2022-09-13 | 2022-09-19 | 100%
| Develop two business cases | ALL | 2022-09-13 | 2022-09-19 | 100%
| Develop Project Initiation Document (PID) | ALL | 2022-09-20 | 2022-10-30 | 100%
| Produce initial Project Plan, RACI | Zo DiSanto | 2022-09-20 | 2022-10-02 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Melika Zandikarimi | 2022-10-11 | 2022-10-16 | 0%
| Produce Context Diagram, Define System Interfaces | Jianan Jiang | 2022-10-11 | 2022-10-16 | 100%
| Define Business Requirements | Melika Zandikarimi | 2022-10-11 | 2022-10-15 | 0%
| Agree to System Requirements types | ALL | 2022-10-15 | 2022-10-16 | 0%
| Define Functional Decomposition | Jianan Jiang | 2022-10-11 | 2022-10-16 | 0%
| Produce RCT document | Jianan Jiang | 2022-10-18 | 2022-10-23 | 0%
| Decide which features to implement this semester | All | 2022-10-18 | 2022-10-23 | 0%
| Produce analysis diagrams (UML, DFD) | Jianan Jiang | 2022-10-18 | 2022-10-23 | 0%
| Define functional requirements (User Stories) | Jianan Jiang | 2022-10-18 | 2022-10-23 | 0%
| Update Project Plan with additional requirements tasks | Melika Zandikarimi | 2022-10-18 | 2022-10-23 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Shanshan Li | 2022-10-25 | 2022-10-30 | 0%
| Database Design (ERD, Table spec) | Rufan Mirganiyev | 2022-10-25 | 2022-10-30 | 0%
| System Interface Design | Shanshan Li | 2022-11-02 | 2022-11-05 | 0%
| User interface design | Kishore Kanchan | 2022-11-02 | 2022-11-05 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | Shanshan Li | 2022-11-07 | 2022-11-13 | 0%
| Establish code repository in GitHUb | Kishore Kanchan | 2022-11-07 | 2022-11-13 | 0%
| Coding & Implemenation | Shanshan Li & Kishore Kanchan | 2022-11-15 | 2022-11-29 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Louise Ngo | 2022-12-02 | 2022-12-07 | 0%
| Evaluate Features to be Tested | Jianan Jiang | 2022-12-02 | 2022-12-07 | 0%
| Design Test Cases | Louise Ngo | 2022-12-02 | 2022-12-07 | 0%
| Execute Test Cases | Louise Ngo | 2022-12-02 | 2022-12-07 | 0%
| Anaylze Test Results | ALL | 2022-12-09 | 2022-12-13 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2022-12-15 | 2022-12-23 | 0%